## Updated Breakup Technical-Task
Track: <<Track>> - Detailed RACI for Stories & Tasks
RACI Legend
R | Responsible | This role has primary responsibility for performing the activities.
A | Accountable | This role will be called to account if the deliverables do not materialize. This is the budget holder/sponsor.
S | Supportive | This role actively assists with the design, implementation or management of the activities.
C | Consulted | This is a hands-off role, offering guidance to those more actively involved.
I | Informed | This role has an interest in the status of the deliverables and should be kept informed of the situation.
Phase | This is the Phase from the Track's ADO / Plan
Story | Stories from the Track's ADO / Plan are covered here. The tasks in the next column should be aligned to the Stories.
Prerequisites | List what must be done or must have happened before proceeding with this Story. If there are no unique prerequisites, assume prior Story completion is the only prerequiste.
Tasks | All tasks to complete the Story as per the ADO / Plan are covered here.
Detailed Steps | These are subtasks for each of the tasks that complete the Story.
Phase | Story | Pre-requisites for the Story | Task: What to Do | Detailed Steps | Joining Firm |  | ITPN |  | GTA |  |  |  |  | Vendor
[5 empty] | Technical Engineer (Hands on the key board) | Decision Maker (Infosec Leader) | Track Lead/ Technical Engineer | PM | Technical Engineer (Hands On the key board) | InfoSec M&A Integration Lead | InfoSec Operations/ Service Delivery Lead | InfoSec Platform Engineering Lead | InfoSec M&A Decision Maker/ PM | Technical Engineer | PM / Account Leader
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please ensure this is the Phase from your ADO / Plan
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please make sure that all your Stories from your ADO / Plan are covered here. And the tasks in the next column should be aligned to the Stories.
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please list what must be done or must have happened before proceeding with this Story.
Note on D15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please make sure that all your tasks from your ADO / Plan are covered here.

## CrowdStrike
Track: <<CrowdStrike>> - Detailed RACI for Stories & Tasks
RACI Legend
R | Responsible | This role has primary responsibility for performing the activities.
A | Accountable | This role will be called to account if the deliverables do not materialize. This is the budget holder/sponsor.
S | Supportive | This role actively assists with the design, implementation or management of the activities.
C | Consulted | This is a hands-off role, offering guidance to those more actively involved.
I | Informed | This role has an interest in the status of the deliverables and should be kept informed of the situation.
Phase | This is the Phase from the Track's ADO / Plan
Story | Stories from the Track's ADO / Plan are covered here. The tasks in the next column should be aligned to the Stories.
Prerequisites | List what must be done or must have happened before proceeding with this Story. If there are no unique prerequisites, assume prior Story completion is the only prerequiste.
Tasks | All tasks to complete the Story as per the ADO / Plan are covered here.
Detailed Steps | These are subtasks for each of the tasks that complete the Story.
Phase | Story | Pre-requisites for the Story | Task: What to Do | Detailed Steps | Joining Firm |  | ITPN |  | GTA |  |  |  |  | Vendor
[5 empty] | Technical Engineer (Hands on the key board) | Decision Maker (Infosec Leader) | Track Lead/ Technical Engineer | PM | Technical Engineer (Hands On the key board) | InfoSec M&A Integration Lead | InfoSec Operations/ Service Delivery Lead | InfoSec Platform Engineering Lead | InfoSec M&A Decision Maker/ PM | Technical Engineer | PM / Account Leader
Discovery | [XX][CS] Discovery - Governance & Scope Alignment | Project kickoff completed. Executive sponsor identified. Stakeholders assigned. Parent/Child CID strategy confirmed. High-level scope and objectives approved. |  | Define implementation scope, Falcon Complete operating model, governance ownership, stakeholder alignment, and deployment responsibilities across Parent/Child CID architecture. | C | I | R | S | C | A | C | C | I | S | I
|  |  | [XX][CS][DSC] Conduct Project Kickoff | Align GT SOC, GT Entity, ITPN, Vendor, and Falcon Complete operational model, deployment phases, and governance checkpoints. | I | C | R | S | C | A | I | C | C | S | S
|  |  | [XX][CS][DSC] Define Scope & Responsibilities | Define deployment ownership, EDR/MDR scope, Parent vs Child CID governance, escalation ownership, and operational support responsibilities. | C | C | R | S | C | A | C | C | C | S | I
|  |  | [XX][CS][DSC] Define Operating Model | Define Falcon Complete detection workflow, GT SOC approval process, incident escalation, ServiceNow workflow, and operational support boundaries. | I | C | C | S | C | A | R | C | C | S | I
| [XX][CS] Discovery - Environment & Readiness Assessment | Governance scope approved. Endpoint inventory available. Network and infrastructure information provided. Required technical contacts identified. Access to existing security tools available. |  | Validate deployment readiness, endpoint inventory, deployment tooling, integration prerequisites, and compliance baseline requirements. | R | I | R | C | C | A | C | C | I | S | I
|  |  | [XX][CS][DSC] Assess Endpoint & Security Environment | Validate endpoint inventory, operating system coverage, legacy AV/EDR tools, coexistence requirements, and exclusion dependencies. | R | I | R | C | C | A | C | C | I | S | I
|  |  | [XX][CS][DSC] Validate Baseline Deployment Methods | Validate Intune, SCCM/MECM, scripted deployment, manual installation process, VDI deployment approach, and server deployment readiness. | C | I | R | C | C | C | I | A | I | S | I
|  |  | [XX][CS][DSC] Validate Network & SIEM Connectivity | Validate firewall access, Falcon Cloud connectivity, proxy configuration, LogScale integration readiness, and API communication requirements. | R | I | R | C | R | C | I | A | I | S | I
|  |  | [XX][CS][DSC] Validate CID & RBAC Readiness | Define Parent/Child CID structure, RBAC model, SSO/MFA integration, audit logging, and compliance readiness. | I | C | C | I | R | C | C | A | I | S | I
|  |  | [XX][CS][DSC] Assess External Security Data Connection Requirements | Identify required external security tools, log sources, incident integrations, and connector dependencies required for SOC visibility and alert correlation. | C | I | R | C | R | A | C | C | I | S | I
Planning | [XX][CS] Planning - Deployment & Governance Strategy | Discovery activities completed. Deployment readiness assessed. Target endpoint inventory validated. Governance and change management process agreed. |  | Define deployment execution approach, governance checkpoints, operational controls, and deployment sequencing strategy. | C | C | R | R | C | A | C | C | C | S | I
|  |  | [XX][CS][PLN] Define Deployment Strategy | Define pilot rollout, phased deployment waves, workstation/server rollout approach, regional sequencing, and fallback deployment methods. | C | C | R | R | C | A | C | C | C | S | I
|  |  | [XX][CS][PLN] Define Operational Governance | Define Falcon Complete workflow, GT SOC governance checkpoints, escalation approvals, incident ownership, and approval process. | I | C | C | R | C | A | R | C | C | S | I
|  |  | [XX][CS][PLN] Define Rollback & Recovery Strategy | Define rollback procedures, deployment recovery workflows, exception handling process, and deployment recovery approvals. | I | C | R | C | R | A | C | C | I | S | I
|  |  | [XX][CS][PLN] Define Compliance & Governance Controls | Define exclusions governance, KPI metrics, operational audit controls, compliance policies, and governance checkpoints. | I | C | C | C | C | A | R | R | C | S | I
|  |  | [XX][CS][PLN] Define External Connector Deployment Dependencies | Define onboarding sequencing and project dependencies for external security connectors aligned to dependent project schedules. | C | I | R | C | R | A | C | C | I | S | I
Design | [XX][CS] Design - Falcon Architecture & Security Controls | Deployment strategy approved. Architecture requirements documented. Integration requirements identified. Security and compliance requirements confirmed. |  | Design Falcon architecture, deployment standards, security controls, integrations, and operational monitoring model. | I | C | C | I | R | C | C | A | I | S | I
|  |  | [XX][CS][DSN] Design CID Architecture & Access Controls | Design Parent/Child CID model, RBAC governance, endpoint grouping, tagging standards, and operational segregation model. | I | C | C | I | R | C | C | A | I | S | I
|  |  | [XX][CS][DSN] Design Security Policies & Monitoring | Design prevention policies, detections, sensor update policies, exclusions, monitoring workflows, and Falcon Complete operational alignment. | I | C | C | I | R | C | C | A | I | S | I
|  |  | [XX][CS][DSN] Design SIEM & External Data Integration | Design LogScale integration, external connector onboarding model, data ingestion, alert correlation, incident integration, and reporting architecture. | I | C | R | I | R | A | C | C | I | S | I
|  |  | [XX][CS][DSN] Design ServiceNow & Incident Workflow | Design incident playbooks, ServiceNow integration workflow, approval process, escalation model, and operational ticket lifecycle management. | I | C | R | I | R | A | R | C | I | S | I
|  |  | [XX][CS][DSN] Design Deployment Standards & Packaging | Design Intune packages, SCCM deployment collections, scripted deployment packages, manual deployment standards, and server deployment approach. | I | I | R | C | R | C | I | A | I | S | I
Configuration | [XX][CS] Configuration - Falcon Platform & Integration Setup | Falcon tenant provisioned. Administrative access granted. Required licenses assigned. Service accounts created. Network/firewall prerequisites completed. Integration endpoints available. |  | Configure Falcon platform, deployment tooling, baseline integrations, and governance controls required for production deployment readiness. | I | I | R | C | R | C | I | A | I | S | I
|  |  | [XX][CS][BLD] Configure Falcon Tenant & Access Controls | Configure Parent/Child CID structure, RBAC, SSO, MFA, endpoint groups, and audit logging controls. | I | I | R | C | R | C | I | A | I | S | I
|  |  | [XX][CS][BLD] Configure Security Policies & Detections | Configure prevention policies, detections, exclusions, monitoring policies, and Falcon Complete operational workflows. | I | I | R | C | R | C | I | A | I | S | I
|  |  | [XX][CS][BLD] Configure Baseline SIEM Integration | Configure LogScale onboarding, baseline Falcon data ingestion, alert forwarding, operational dashboards, and SOC visibility requirements. | I | I | R | C | R | A | R | C | I | S | I
|  |  | [XX][CS][BLD] Prepare External Security Data Connections | Prepare external connector configurations, API onboarding requirements, ingestion mappings, and deployment prerequisites for future integration enablement. | C | I | R | C | R | A | C | C | I | S | I
|  |  | [XX][CS][BLD] Prepare Deployment Packages & Tooling | Configure deployment packages, deployment tokens, Intune integration, SCCM/MECM integration, scripted deployment methods, and AV removal readiness. | I | I | R | C | R | C | I | A | I | S | I
| [XX][CS] Configuration - Falcon Rollout Execution | Platform configuration completed. Installation packages and deployment tools validated. Pilot deployment approved. Change window scheduled. Rollback plan documented. |  | Execute Falcon deployment rollout across endpoints, servers, and critical systems while validating deployment health and operational readiness. | S | I | R | R | R | C | C | A | I | S | I
|  |  | [XX][CS][BLD] Execute Pilot Deployment | Deploy Falcon sensors to pilot endpoints using approved deployment methods and validate deployment health. | S | I | R | C | R | C | I | A | I | S | I
|  |  | [XX][CS][BLD] Execute Production Workstation Rollout | Execute phased deployment rollout across production workstations and user endpoints using Intune, SCCM/MECM, or approved deployment tooling. | S | I | R | C | R | C | I | A | I | S | I
|  |  | [XX][CS][BLD] Execute Server & Critical System Rollout | Execute deployment rollout across servers and critical workloads using approved maintenance windows and deployment standards. | S | I | R | C | R | C | I | A | I | S | I
|  |  | [XX][CS][BLD] Execute Exception & Manual Deployment Activities | Deploy Falcon sensors to isolated systems, VDI systems, exception devices, and manually managed endpoints. | S | I | R | C | R | C | I | A | I | S | I
|  |  | [XX][CS][BLD] Validate Sensor Visibility & Health | Validate endpoint visibility, sensor connectivity, policy assignment, telemetry communication, and reporting status. | S | I | R | C | R | C | C | A | I | S | I
Validation | [XX][CS] Validation - Security Operations & Testing | Deployment completed on target systems. Required integrations operational. Test cases prepared. GT SOC stakeholders available for validation. |  | Validate detections, integrations, operational workflows, deployment quality, performance, and GT SOC operational readiness. | S | I | R | C | R | A | R | C | C | S | I
|  |  | [XX][CS][TST] Validate Security Operations Workflow | Validate detections, approvals, incident response workflow, ServiceNow integration, SIEM alerts, and audit trail logging. | S | I | R | C | R | A | R | C | I | S | I
|  |  | [XX][CS][TST] Execute Security Validation Testing | Execute coexistence validation, detection tuning, operational alert validation, and red team simulation testing. | S | I | R | C | R | A | C | C | I | S | I
|  |  | [XX][CS][TST] Execute Rollback & Recovery Testing | Execute rollback validation, deployment recovery testing, and operational recovery workflow validation. | S | I | R | C | R | A | C | C | I | S | I
|  |  | [XX][CS][TST] Validate Performance & Data Quality | Validate endpoint performance, network impact, SIEM ingestion quality, telemetry visibility, and log data quality. | S | I | R | C | R | A | C | C | I | S | I
|  |  | [XX][CS][TST] Validate Connector Readiness & Dependency Tracking | Validate external connector readiness status and confirm deferred integrations do not impact GT SOC operational hand-off. | I | I | R | C | R | A | R | C | I | S | I
Cutover | [XX][CS] Cutover - Go-Live | Validation successfully completed. Critical issues resolved. Customer go-live approval received. Monitoring and support resources available. |  | Complete operational transition, governance hand-off, go-live approval, and hypercare stabilization support. | I | C | R | R | C | C | A | C | C | S | I
|  |  | [XX][CS] [CUT] Deliver Documentation & Knowledge Transfer | Deliver architecture documentation, deployment runbooks, operational workflows, KPI metrics, and conduct knowledge transfer sessions. | S | I | R | C | R | C | A | C | I | S | I
|  |  | [XX][CS] [CUT] Complete Governance Transition | Transfer GT SOC governance ownership, validate operational readiness, and confirm support transition requirements. | I | C | R | C | C | C | A | C | C | I | I
|  |  | [XX][CS] [CUT] Execute Go-Live Validation | Complete final deployment validation, asset certification, governance approval, and executive readiness review. | I | C | R | R | C | C | C | C | A | I | I
|  |  | [XX][CS] [CUT] Execute Hypercare & Stabilization Support | Provide post-go-live stabilization support, KPI monitoring, operational tuning, and deployment issue remediation. | I | I | R | C | R | C | A | C | I | S | I
|  |  | [XX][CS] [CUT] Transition Deferred Integration Roadmap | Transition outstanding external connector onboarding activities and dependency tracking into operational backlog and project governance. | I | I | C | R | C | A | R | C | C | S | I
Hand-Off | [XX][CS] Hand-Off - Operational Transition | Go-live completed successfully. Documentation finalized. Knowledge transfer completed. Operational support contacts established. Acceptance criteria met. |  | Transition operational ownership to support and operations teams. | S | C | R | C | C | C | A | C | I | I | I
|  |  | [XX][CS] [HND] - Create / all documents associated to entity | Create or update operational runbooks and support documentation. | S | I | R | C | R | C | A | C | I | S | I
|  |  | [XX][CS] [HND] - Training & Transition to Operations | Deliver operational training and transition support responsibilities. | S | I | R | C | R | C | A | C | I | S | I
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please ensure this is the Phase from your ADO / Plan
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please make sure that all your Stories from your ADO / Plan are covered here. And the tasks in the next column should be aligned to the Stories.
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please list what must be done or must have happened before proceeding with this Story.
Note on D15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please make sure that all your tasks from your ADO / Plan are covered here.